## Overview
SmartCommute PH — Prototype Sprint
Group 11 · BSCS · PUP CCIS · task delegation & timeline
Goal | Working prototype for panel — finished the soonest (target ~1 month: Jul 13 - Aug 15).
Start | Monday, July 13, 2026 (kickoff meeting)
Weekly check-in | Every Saturday — Jul 18, Jul 25, Aug 1, Aug 8, Aug 15
UI/UX dashboard due | Saturday, July 18, 2026 (hard sub-deadline)
Hard deadline | Saturday, August 15, 2026 (final check-in — defense-ready)
Discipline | Strict. Deadlines are gates — a task is not done until QA (Dave) signs off.
Repo | github.com/andrei13spot/smartcommuteph
Owners
Member | Role | Owns | Tasks
Luis | Full Front End (Figma + Bootstrap 5) | All 4 screens, design system, copy voice | 12
Andrei | Backend Lead (Node + Express + A* core) | Routing service, algorithm, API contract, benchmark | 14
Princess | ML Components + Backend Support (Python) | AHP weights, model support, graph attrs, docs | 6
Dave | QA Lead + Data Pipeline Check | Sign-off before merge, pruning & comparison checks | 8
Status legend
Not started
In progress
Blocked
Done
★ Milestone

## Git workflow
Git workflow — everyone follows this
Always branch off dev. Never commit straight to main or dev.
Before you start ANY task — always:
git checkout dev
git pull origin dev
git checkout -b <branch> # branch off the latest dev
Branch | Purpose | Rule
main | Release / defense-ready | Updated only at Saturday gates, after QA sign-off. Never commit directly.
dev | Integration branch | Everything merges here first via Pull Request. Never commit directly.
feature branch | One per task | Branched off the latest dev; deleted after it merges.
Area | Branch prefix | Examples
Front end | fe/ | fe/route-query, fe/compare-view
Backend / algorithm | be/ | be/astar-core, be/compare-endpoint
ML | ml/ | ml/ahp-weights, ml/lstm-ridership
QA / tests | qa/ | qa/comparison-check
• Commit small and often; lowercase messages.
• Push your branch: git push -u origin <branch>.
• Open a Pull Request into dev. Dave (QA) reviews & signs off BEFORE it merges into dev.
• Release: dev -> main only at the Saturday check-in gates, once QA has signed off.

## Timeline
Timeline — 4 sprints + buffer
Mon Jul 13 → Sat Aug 15, 2026 · Saturday check-ins
Sprint / week | Dates | Focus | Saturday gate
Kickoff | Mon Jul 13 | Align on API contract; assign; Figma finalized from mockup v4. | —
Week 1 | Jul 13 – Jul 18 | FRONT END BUILD. Luis: all 4 screens in Bootstrap 5 + design system + copy fixes. Andrei: lock API contract, Express skeleton, graph static attrs. Princess: start AHP matrices. Dave: test plan. | Sat Jul 18 — ★ UI/UX dashboard COMPLETE; API contract locked & documented.
Week 2 | Jul 20 – Jul 25 | ROUTING CORE. Andrei: multi-criteria A*, node counter, distance baseline, transfer friction, /route + /compare. Princess: deliver 4 AHP weight vectors. Luis: wire UI to live API. Dave: QA harness vs contract. | Sat Jul 25 — A* + baseline + counter live; /route & /compare returning; 4 weight vectors delivered.
Week 3 | Jul 27 – Aug 1 | ML + BENCHMARK. LSTM (ridership) + RFR (flood) integrated; dynamic edges refresh; benchmark harness → 360 rows. Luis: polish comparison view. Dave: comparison check. | Sat Aug 1 — 360-row benchmark with 8 KPIs; routes differ across profiles.
Week 4 | Aug 3 – Aug 8 | QA + FREEZE. Dave: full functional QA, pruning check, data-pipeline check → sign-off. Fixes across team. Integration freeze + dry run. | Sat Aug 8 — Dave sign-off; pruning verified (framework < baseline); integration freeze.
Buffer | Aug 10 – Aug 15 | Defense prep, last fixes, rehearsal, dry runs. No new features. | Sat Aug 15 — ★ Prototype complete & defense-ready (hard deadline).

## Tasks
Master task list
Owner-coded · P1 = must-ship · dates 2026 · status starts 'Not started'
# | Task | Owner | Area | Priority | Start | Due | Status
1 | Kickoff meeting + assign + align on API contract | All | Planning | P1 | 2026-07-13 | 2026-07-13 | Not started
2 | Finalize Figma from mockup v4 | Luis | Design | P1 | 2026-07-13 | 2026-07-15 | Not started
3 | Agree API request/response shape with Andrei | Luis | Handoff | P1 | 2026-07-14 | 2026-07-15 | Not started
4 | Network map render: 10 anchors, 3 rail lines, legend, stat chips | Luis | Front end | P1 | 2026-07-15 | 2026-07-16 | Not started
5 | Route query screen: OD dropdowns, profile selector, validation, loading | Luis | Front end | P1 | 2026-07-16 | 2026-07-17 | Not started
6 | Result view: map, why-this-route, criteria rings, 4 headline stats | Luis | Front end | P1 | 2026-07-17 | 2026-07-18 | Not started
7 | Comparison view: 4 cards, active highlight, transparency frame + cost eq (money shot) | Luis | Front end | P1 | 2026-07-17 | 2026-07-18 | Not started
8 | Design system: color tokens, all states (default/hover/active/disabled/loading/empty/error), responsive | Luis | Design | P1 | 2026-07-15 | 2026-07-18 | Not started
9 | Copy fixes: drop 'reimagined' & the 'live weather' wording -> 'MET Norway rainfall forecast', framework voice | Luis | Copy | P2 | 2026-07-18 | 2026-07-18 | Not started
10 | ★ MILESTONE: UI/UX dashboard COMPLETE | Luis | Milestone | P1 | 2026-07-18 | 2026-07-18 | Milestone
11 | Wire front end to live /route + /compare | Luis | Front end | P1 | 2026-07-20 | 2026-07-25 | Not started
12 | Polish comparison view for panel | Luis | Front end | P1 | 2026-07-27 | 2026-08-01 | Not started
13 | Responsive QA fixes with Dave | Luis | Front end | P2 | 2026-08-03 | 2026-08-08 | Not started
14 | Finalize + document API contract (/route, /compare) | Andrei | API | P1 | 2026-07-13 | 2026-07-15 | Not started
15 | Express routing service skeleton | Andrei | Backend | P1 | 2026-07-15 | 2026-07-17 | Not started
16 | Graph layer: load static attrs at startup (fare, base time, distance, transfer flags) | Andrei | Backend | P1 | 2026-07-16 | 2026-07-18 | Not started
17 | Multi-criteria A*: Eq 3 cost, heuristic v_max 60, mode speeds 40/60/30/20, multiplier 1.0-2.0 | Andrei | Algorithm | P1 | 2026-07-20 | 2026-07-22 | Not started
18 | Node-expansion counter inside the loop (pruning evidence) | Andrei | Algorithm | P1 | 2026-07-22 | 2026-07-23 | Not started
19 | Distance-based A* baseline (locked comparison target) | Andrei | Algorithm | P1 | 2026-07-23 | 2026-07-24 | Not started
20 | Transfer friction TF-prime from 5x5 adjacency matrix | Andrei | Algorithm | P1 | 2026-07-23 | 2026-07-24 | Not started
21 | POST /route: one route + 8 KPIs | Andrei | API | P1 | 2026-07-24 | 2026-07-25 | Not started
22 | POST /compare: 4 profiles + baseline = 5 results | Andrei | API | P1 | 2026-07-24 | 2026-07-25 | Not started
23 | LSTM ridership model (TF + Keras, 24-mo window, eFOI contingency) | Andrei | ML | P1 | 2026-07-20 | 2026-07-29 | Not started
24 | RFR flood-risk model (scikit-learn, MET Norway Locationforecast 24-hour rainfall input) | Andrei | ML | P1 | 2026-07-22 | 2026-07-29 | Not started
25 | Refresh dynamic edges (ridership, flood) at start of each benchmark run | Andrei | Backend | P1 | 2026-07-29 | 2026-07-30 | Not started
26 | Benchmark harness: 45 OD x 4 profiles x 2 algos = 360 rows, 8 KPIs | Andrei | Benchmark | P1 | 2026-07-30 | 2026-08-01 | Not started
27 | Integration + fixes from QA | Andrei | Backend | P1 | 2026-08-03 | 2026-08-08 | Not started
28 | AHP weight derivation (Excel): 150 respondents, Saaty 1-9, normalized col avg, reject CR>=0.10 | Princess | ML | P1 | 2026-07-13 | 2026-07-20 | Not started
29 | Hand 4 AHP weight vectors to Andrei | Princess | Handoff | P1 | 2026-07-20 | 2026-07-20 | Not started
30 | Graph layer support: static attrs + dynamic edge refresh | Princess | Backend | P1 | 2026-07-16 | 2026-07-18 | Not started
31 | Transfer friction: 5x5 adjacency matrix values | Princess | ML | P1 | 2026-07-15 | 2026-07-20 | Not started
32 | LSTM/RFR support + training-data prep | Princess | ML | P1 | 2026-07-22 | 2026-07-29 | Not started
33 | Documentation: methodology, model cards, data sources | Princess | Docs | P2 | 2026-07-27 | 2026-08-08 | Not started
34 | Draft test plan + test cases for all 4 screens | Dave | QA | P1 | 2026-07-15 | 2026-07-18 | Not started
35 | Functional QA of UI/UX dashboard | Dave | QA | P1 | 2026-07-18 | 2026-07-20 | Not started
36 | Set up test harness against API contract | Dave | QA | P1 | 2026-07-20 | 2026-07-25 | Not started
37 | Functional QA: dropdowns=10 anchors, profiles=4, block same/empty OD, loading+error, geometry render | Dave | QA | P1 | 2026-07-27 | 2026-07-31 | Not started
38 | Comparison check: 4 profiles give different routes; flag loud if any two match | Dave | QA | P1 | 2026-07-31 | 2026-08-01 | Not started
39 | Data pipeline: log = exactly 360 rows, 8 KPIs incl. fare with 20% student/senior discount | Dave | QA | P1 | 2026-08-03 | 2026-08-04 | Not started
40 | Pruning check: framework nodes expanded < baseline on pruned queries; flag if not | Dave | QA | P1 | 2026-08-04 | 2026-08-05 | Not started
41 | Final QA sign-off before merge | Dave | QA | P1 | 2026-08-06 | 2026-08-08 | Not started
42 | Integration freeze + full dry run | All | Integration | P1 | 2026-08-08 | 2026-08-08 | Not started
43 | Buffer / defense prep / rehearsal / dry runs | All | Buffer | P1 | 2026-08-10 | 2026-08-15 | Not started
44 | ★ MILESTONE: Prototype complete & defense-ready (hard deadline) | All | Milestone | P1 | 2026-08-15 | 2026-08-15 | Milestone

## Check-ins
Saturday check-ins — gate criteria
A gate is not passed until every item is true. Strict.
Check-in | Date | Must be TRUE to pass the gate
#1 | Sat Jul 18 | ★ UI/UX dashboard COMPLETE — all 4 screens in Bootstrap 5 with all states. API contract locked & documented (Andrei). Express skeleton up; graph layer loads static attrs. AHP matrices in progress (Princess). QA test plan drafted (Dave).
#2 | Sat Jul 25 | Multi-criteria A* + distance baseline + node-expansion counter working. /route and /compare return results (compare = 4 profiles + baseline). 4 AHP weight vectors delivered to Andrei (Princess). Front end wired to live API (Luis). QA harness runs against the contract (Dave).
#3 | Sat Aug 1 | LSTM + RFR integrated; dynamic edges refresh at run start. Benchmark harness produces exactly 360 rows with all 8 KPIs. Comparison view polished (Luis). Comparison check passed — the 4 profiles produce different routes (Dave).
#4 | Sat Aug 8 | Dave full functional QA sign-off. Pruning check passed — framework expands fewer nodes than baseline. Data-pipeline check passed — 360 rows, fare shows 20% student/senior discount. Copy fixes in; responsive pass done. Integration freeze + dry run.
Close | Sat Aug 15 | ★ Prototype complete & defense-ready. Buffer week used only for defense prep, rehearsal, and last fixes — no new features.

## API Contract
API contract (starter) — Andrei owns
Lock with Luis before wiring. Dave tests against this. Anchor ids = the 10 anchors.
Field | Spec
POST /route
Request | { origin: <anchorId>, destination: <anchorId>, profile: 'uncrowded'¦'cheapest'¦'safest'¦'convenient' }
Validation | origin != destination; origin, destination and profile all required (else 400).
Response | { profile, origin, destination, geometry: [[lat,lng], ...], kpis: {...}, why_this_route: <text>, criteria: { T, F, R, P } }
KPIs (8) | 1 travel_time_min · 2 distance_km · 3 fare_php (20% student/senior discount applied where eligible) · 4 transfers · 5 flood_risk_score · 6 ridership_density_score · 7 nodes_expanded · 8 exec_ms
POST /compare
Request | { origin: <anchorId>, destination: <anchorId> }
Response | { origin, destination, results: [ { profile: 'baseline'¦<4 profiles>, geometry, kpis } ] } -> 5 results (4 profiles + distance baseline)
Note | Same KPI block on every result. Baseline = distance-based A* (locked target, not the HAZMAT study).
Benchmark log
Rows | 45 OD pairs x 4 profiles x 2 algorithms = 360 rows. One row per (OD, profile, algorithm).
Columns | od_pair, profile, algorithm, then the 8 KPIs above.